## Sheet1
Activity | Time | [14 empty] | Assign | Responsible for
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Gather all information from user requirement | [15 empty] | Gathering every information from user pass by website just like a Facebook or etc. R4 | Everyone
Make a pre-document for game design | [15 empty] | Create a pre-document for every part in this game to check that our game is cover all necessary information. | Designer
Analyze and fix some information in document | [15 empty] | Analyze and fix any error detail or improve it to make it more effective. | Designer
Finish Gathering information/requirement
High concept | [15 empty] | Brainstorming about main idea and theme of the game | Designer
Concept | [15 empty] | Design and make a storyboard and major gameplay mechanics | Designer
Design | [15 empty] | Design character and all the environment | Artist
Experiment | [15 empty] | Conduct a test for current idea and state of the game | Programmer
Finish Pre-production
Programming | [15 empty] | Coding on gameplay mechanics | Programmer
Create database | [15 empty] | Create database for this game | Programmer
Connect database to game | [15 empty] | Connect database to the game | Programmer
Art production | [15 empty] | Make models, objects, and maps | Artist
Level creation | [15 empty] | Implement the models, objects, and map into one single playable map | Level designer
Audio production | [15 empty] | Input song and sound effect | Sound engineer
Create template | [15 empty] | Create template of web that use for this game | Artist
Finish production
Code freeze | [15 empty] | Fix all game content that are glitches also include major bugs | Tester
Code release | [15 empty] | Fix all minor bugs | Tester
Finish testing
Documentation | [15 empty] | Make a documentation on project report | Everyone
Presentation preparing | [15 empty] | Prepare of presentation | Everyone
Documentation